## WorkingList
Working group | Report Section | Priority | Request | Source | Progress | Products/ things to work on | New Data opportunities | Notes
All | All | Highest | Uncertainty estimates for all indicators | Both Councils | SOE survey biomass | Indicator specific uncertainty estimates
All | All | Improve communciation | Include Downeast ME (Scotian Shelf EPU) | NEFMC | SOE survey biomass, and many indicators include | Ask Council/SSC |  | include as SS or combined SS and GOM? SSC comment just says to clarify, could continue with current GOM
Climate/LTL/Habitat | Habitat Quality and Ecosystem Productivity | High | Link zooplankton abundance and or comunity composition to fish condition | NEFMC | SOE 2 pager, explain ongoing research in memo | Synthesize existing indicators | Add longline survey condition? | both already in this section
Climate/LTL/Habitat | Habitat Quality and Ecosystem Productivity | Highest | OA | Both Councils | not enough yet sampling table in memo? |  |  | At least report on efforts if data are not there yet
Climate/LTL/Habitat | Habitat Quality and Ecosystem Productivity | Improve communciation | Gulf Stream Index/Labrador current interaction | Both Councils | SOE eco conditoins NEFMC | Heat wave stuff (Vince) |  | Already in report, integrate with other indicators?
Climate/LTL/Habitat | Habitat Quality and Ecosystem Productivity | Improve communciation | Include source for PP estimates (satellite vs in situ) | NEFMC | SOE add to text satellite |  |  | Easy, just clarify in report
Climate/LTL/Habitat | Fish and Invertebrates LINK TO Habitat Quality and Ecosystem Productivity | Moderate | Shellfish growth'dist linked to climate (system productivity) | MAFMC | project with R Mann student to start late 2020? in memo | Heat wave stuff (Vince) | (Roger Mann VIMS data Contribution)
Climate/LTL/Habitat | Economic and Social (new section Other Ocean Uses?) | Moderate | Esturine condition relative to power plants and temp | MAFMC |  |  | (McKinney 2010, Kim Hyde also on this paper)
Climate/LTL/Habitat | Habitat Quality and Ecosystem Productivity | Moderate | Frequency and occurance of warm rings | MAFMC | SOE added indicator | Heat wave stuff (Vince)
Climate/LTL/Habitat | Habitat Quality and Ecosystem Productivity | Moderate | Cold pool index | MAFMC | SOE added indicator | Heat wave stuff (Vince)
Climate/LTL/Habitat | Habitat Quality and Ecosystem Productivity | High (Mid) | Nutrient inputs and water quality near shore | MAFMC | NERRs summary started discuss in memo |  | NERR network? Chesapeake Bay water quality (existing), ECOMON (tried last year, try again?) | Also, get from EPA report? Nearshore habitat risk assessment element
Climate/LTL/Habitat and Human dimension | Economic and Social LINK TO Habitat Quality and Ecosystem Productivity | HIgh | Link environmental and social, economic indicators | NEFMC | SOE habitat wind overlap, 2 pager conceptual model | Syntheisis
Climate/LTL/Habitat and Human dimension | Economic and Social (new section Other Ocean Uses?) | High (Mid) | Quantitative overlap of wind area and habitat and fishing areas | MAFMC | SOE habitat wind overlap, wind overlap with fisheries for next round |  | Kevin habitat occupancy and trends in lease areas, Geret effort in lease areas, BOEM hotspot analyses? | MAFMC Risk Assessment need
Comm + everyone | Summary | Highest | Report card like alaska | Both Councils | SOE 2 pager bullets | 2 pager |  | Top three points! 1.Ecosystem->fisheries productivity (Focus on LTL - Nutrient imput to fish production MA very interested how to create synthetic narrative), 2. ocean heat waves (currents/setup, impacts)? 3. other ocean uses/wind MA 3. ecosystem and right whales NE?
Comm + everyone | Summary | Highest | Summary visualization | Both Councils | SOE 2 pager graphics | Infographic
Comm + everyone | Head of each Report Section, also Summary? | Highest | Formal response to requests | Both Councils | this response memo | Create forum for formal response |  | Changes at request of Councils. What is new/Top 3 points for the section
Human dimension | Economic and Social | Done | Include links to Social Science websites | NEFMC | SOE NEFMC (add to mid) |  |  | did for Council 2019 report
Human dimension | MAFMC Risk Assessment | High (Mid) | Management complexity | MAFMC | work started by summer student, needs further analysis | Complete current project | Summer student project last year
Human dimension | Economic and Social | High (Mid) | South atlantic managed species represented in recreational indices - break out species managed by MA, SA and AS. | MAFMC | SOE revised rec catch diversity |  | SSB to determine
Human dimension | Summary | See summary | Add social elements from overview conceptual model to NE conceptual model | NEFMC | older general conceptual model repoaced by specific links between indicators in report | Conceptual model update |  | Could just cut and paste from NE Shelf to MA and GOM/GB, but whole infographic may be done over
Megafauna | Fish and Invertebrates LINK TO Habitat Quality and Ecosystem Productivity | High | Avg weight of diet components by feeding group | Both Councils | stomach fullness analysis started--species level | Food habits summaries | Bigelow + NEAMAP + longline + seabirds? | If jellies show up as fluctuating, could be a place to link abundance time series in
Megafauna | Protected Species | High | North Atlantic Right Whale calf production indicator | NEFMC | SOE added indicator | Contact Chris Orphanides (PSB) | (Gutbrod et al 2015)
Megafauna | Document Orientation; Economic and Social; Fish and Invertebrates | Improve communciation | Distinguish managed species in report | NEFMC | SOE council managed species in figs, table |  |  | Table 2 attempted this; figures separate council managed and all seafood, revenue, and biomass; needs more emphasis?
Megafauna | Protected Species | Moderate | Marine Mammal consumption | MAFMC | SOE added discussion of seal diets, memo no new consumption ests since Smith et al but could be in the future once work is complete |  | Herring Assessment | possibly came from 2012 herring assessment, ask Laurel
Megafauna | Fish and Invertebrates | Moderate | Small pelagic abundance | MAFMC | SOE have survey planktivore time series but would like to improve |  | Combine herring, mackerel, menhaden, other assessments? | already include planktivore survey indices; previous index possibly came from ESR as survey index, problematic from assessment standpoint;
Megafauna | Fish and Invertebrates | Moderate | Young of Year index from multiple surveys | MAFMC | SOE fish production from NEFSC trawl, want to expand this? |  | Bigelow + NEAMAP + CHESMAP/other state surveys? + seabirds? | Evaluate resources to do
Megafauna | Fish and Invertebrates | Moderate | Biomass of sharks | MAFMC | HMS got us landings for 3 years, need more time to get time series, still looking for source of biomass data |  | HMS assessments
Megafauna | Fish and Invertebrates | Moderate | Diversity metric for NEFSC trawl survey | NEFMC | still need to reconcile different vessel catchabilites |  | Bigelow + other state surveys?
Megafauna | Fish and Invertebrates LINK TO Habitat Quality and Ecosystem Productivity | Moderate | Mean stomach weight across feeding guilds | MAFMC | stomach fullness analysis started--species level | Food habits summaries | Bigelow + NEAMAP + longline + seabirds?
Thresholds/methods | Summary | Highest | Ecosystem risk score | MAFMC | working towards with PP required could do other metrics ask for specific feedback | Multivariate stuff | All datasets
Thresholds/methods | All | Highest | Inflection points for indicators | Both Councils | threshold analysis? | Determining thresholds | All datasets
ECSA | Dont lose this comment but not relevant to SOE update |  | SSC would like to review ECSA | NEFMC | Forward to Scott
Expectations for September 26 call
All subgroups - What indicators are you using this year? Is it all available?
Methods - What anaylsis are we using and a demo using last year's data
Comms - Workup of 2 pager, Ideas and progress made with infographic

## MemoTable
Request | Source | Progress | Memo Section
Formal response to requests | Both Councils | this response memo | Introduction
Consider report card like Alaska's | Both Councils | SOE summary bullets (page 1) | 1
include summary visualization | Both Councils | SOE infographics (page 2) | 2
Include uncertainty estimates for all indicators | Both Councils | SOE survey biomass uncertainty included; feedback requested for other indicators | 3
Include Downeast ME (Scotian Shelf EPU) | NEFMC | SOE survey biomass now includes most; included in other indicators | 4
Link zooplankton abundance and or community composition to fish condition | NEFMC | SOE page 2 research spotlight | 5
Ocean acidification information | Both Councils | inadequate information for indicator; existing info summarized here | 6
Gulf Stream Index/Labrador current interaction | Both Councils | SOE Labrador current and Gulf Stream indices now included in both reports | 7
Include source for PP estimates (satellite vs in situ) | NEFMC | SOE clarified that all PP estiamtes are from satellite | 8
Shellfish growth/distribution linked to climate (system productivity) | MAFMC | project with R. Mann student to start late 2020 | 9
Esturine condition relative to power plants and temp | MAFMC | inadequate resourses to address this year | 10
Frequency and occurance of warm rings | MAFMC | SOE added indicator | 11
Cold pool index | MAFMC | SOE added indicator | 12
Nutrient inputs and water quality near shore | MAFMC | summary of data from National Estuarine Research Reserve network started, example info included here | 13
Link environmental and social, economic indicators | NEFMC | SOE habitat wind overlap, page 2 conceptual model | 14
Quantitative overlap of wind area and habitat and fishing areas | MAFMC | SOE habitat wind overlap, wind overlap with fisheries for next round | 15
Include links to Social Science websites | NEFMC | SOE link included in both reports | 16
Management complexity | MAFMC | project started by summer student in 2018, needs further analysis | 17
South atlantic managed species represented in recreational indices - break out species managed by MA, SA and AS. | MAFMC | SOE revised indicator and noted change in report | 18
Add social elements from overview conceptual model to NE conceptual model | NEFMC | older general conceptual model replaced by specific links between indicators in report | 19
Avg weight of diet components by feeding group | Both Councils | stomach fullness analysis started--species level; feedback requested | 20
North Atlantic Right Whale calf production indicator | NEFMC | SOE added indicator | 21
Distinguish managed species in report | NEFMC | SOE Council managed species separated in landings figures | 22
Marine Mammal consumption | MAFMC | SOE added discussion of seal diets | 23
Small pelagic abundance | MAFMC | SOE have survey planktivore time series but would like to improve; see also SOE forage energy density | 24
Young of Year index from multiple surveys | MAFMC | SOE fish production from NEFSC trawl; feedback reqested on how to expand | 25
Biomass of sharks | MAFMC | HMS provided landings for 3 years and working on full time series, still looking for source of biomass data | 26
Diversity metric for NEFSC trawl survey | NEFMC | need to reconcile different survey vessel catchabilites or split by vessel | 27
Mean stomach weight across feeding guilds | MAFMC | stomach fullness analysis started--species level; feedback requested | 28
Ecosystem risk score | MAFMC | SOE PP required a step towards this; feedback requested for other desired analyses | 29
Inflection points for indicators | Both Councils | inadequate resources to do inflection point and threshold analysis this year | 30